## Config
Setting | Value
Today | 2026-09-11
Critical score threshold | 150
Approaching risk threshold | 110
Decision threshold | 85
Finance freshness warning days | 30
Finance freshness critical days | 60
Default internal lead days | 14
Default data request lead days | 23
Default finance lead days | 13
Default draft lead days | 8
Default review lead days | 5
Portfolio owner | Associate Director
NOTE | Sample data only. Replace with production values when connected.

## Grants
Grant ID | Grant Name | Funder | Program | Grant Number | Award Amount | Start Date | End Date | Grant Manager | Responsible Executive | Program Owner | Finance Contact | Funder Contact | Lifecycle Status | Renewal Date | Source Documents URL | Authoritative Finance Source | Notes
G-001 | SAMPLE — Community Services Grant | Public Agency | Community Support | SAMPLE-001 | 250000 | 46023 | 46387 | Associate Director | Executive Director | Program Director | Finance Lead | Funder PM | Active | 46341 |  | Accounting system | Synthetic test case
G-002 | SAMPLE — Family Stabilization Grant | Community Funder | Family Services | SAMPLE-002 | 125000 | 46113 | 46477 | Associate Director | Executive Director | Program Director | Finance Lead | Program Officer | Active | 46402 |  | Accounting system | Synthetic test case
G-003 | SAMPLE — Capacity Building Grant | Private Foundation | Operations | SAMPLE-003 | 60000 | 46204 | 46568 | Associate Director | Executive Director | Operations Director | Finance Lead | Program Officer | Active | 46447 |  | Accounting system | Synthetic test case

## Requirements
Requirement ID | Grant ID | Requirement | Category | Funder Deadline | Internal Deadline | Recurrence | Responsible Person | Reviewer | Dependency Summary | Status | Source Document URL | Source Citation/Page | Evidence Required? | Evidence Status | Verification Status | Notes
R-001 | G-001 | Quarterly narrative report | Reporting | 46282 | 46279 | Quarterly | Associate Director | Executive Director | Program data + finance data | In Progress |  | § / page TBD | Yes | Missing | Verified | Synthetic
R-002 | G-001 | Quarterly financial report | Financial | 46282 | 46279 | Quarterly | Finance Lead | Associate Director | Current ledger extract | At Risk |  | § / page TBD | Yes | Missing | Verified | Synthetic
R-003 | G-002 | Participant outcome update | Deliverable | 46310 | 46303 | Quarterly | Program Director | Associate Director | Outcome metric refresh | Not Started |  | § / page TBD | Yes | Missing | Verified | Synthetic
R-004 | G-003 | Renewal go/no-go decision | Renewal | 46283 | 46281 | Annual | Executive Director | Associate Director | Leadership decision | Decision Needed |  | § / page TBD | No | N/A | Verified | Synthetic
R-005 | G-001 | Insurance certificate maintained | Compliance | 46357 | 46341 | Annual | Operations Director | Associate Director | Current COI | Not Started |  | § / page TBD | Yes | Missing | Verified | Synthetic
R-006 | G-002 | Final closeout package | Closeout | 46507 | 46487 | One-time | Associate Director | Executive Director | Final program + financial reports | Not Started |  | § / page TBD | Yes | Missing | Verified | Synthetic

## Milestones
Milestone ID | Grant ID | Requirement ID | Milestone | Milestone Type | Date | Owner | Status | Calendar Event ID | Notes
M-001 | G-001 | R-001 | Program data due | Dependency | 46275 | Program Director | Overdue |  | Synthetic
M-002 | G-001 | R-002 | Finance data due | Dependency | 46276 | Finance Lead | Due |  | Synthetic
M-003 | G-001 | R-001 | Executive review | Approval | 46279 | Executive Director | Upcoming |  | Synthetic
M-004 | G-001 | R-001 | Funder report due | External deadline | 46282 | Associate Director | Upcoming |  | Synthetic
M-005 | G-003 | R-004 | Renewal decision | Decision | 46281 | Executive Director | Upcoming |  | Synthetic
M-006 | G-003 | R-004 | Renewal external date | External deadline | 46283 | Associate Director | Upcoming |  | Synthetic
M-007 | G-002 | R-003 | Outcome data refresh | Dependency | 46303 | Program Director | Upcoming |  | Synthetic

## Tasks
Task ID | Grant ID | Requirement ID | Task | Owner | Due Date | Reviewer | Status | Dependency Task ID | Dependency Status | Evidence Required? | Evidence Status | Associate Director Action? | Severity | Escalation Status | Notes | Priority Score | Rank Key
T-001 | G-001 | R-001 | Obtain participant/program data | Program Director | 46275 | Associate Director | Overdue |  |  | No | N/A | No | High | Escalated | Program data was due yesterday | 135 | 135
T-002 | G-001 | R-002 | Obtain current finance data | Finance Lead | 46276 | Associate Director | Not Started |  |  | No | N/A | No | Critical | Escalated | Required for report | 135 | 135
T-003 | G-001 | R-001 | Draft narrative report | Associate Director | 46278 | Executive Director | Blocked | T-001 | Overdue | No | N/A | Yes | High | Open | Blocked by program data | 195 | 195
T-004 | G-001 | R-002 | Review financial report | Associate Director | 46279 | Executive Director | Not Started | T-002 | Not Started | Yes | Missing | Yes | Critical | Open | Finance source stale | 235 | 235
T-005 | G-003 | R-004 | Make renewal go/no-go decision | Executive Director | 46281 | Associate Director | Decision Needed |  |  | No | N/A | Yes | Medium | Open | Leadership decision needed | 150 | 150.0001
T-006 | G-001 | R-001 | Submit quarterly report | Associate Director | 46282 | Executive Director | Not Started | T-003 | Blocked | Yes | Missing | Yes | Critical | Open | External deadline | 220 | 220.0001
T-007 | G-002 | R-003 | Refresh participant outcome metric | Program Director | 46303 | Associate Director | Not Started |  |  | No | N/A | No | Medium | None |  | 25 | 25.0001
T-008 | G-002 | R-003 | Review deliverable trajectory | Associate Director | 46280 | Program Director | Not Started | T-007 | Not Started | No | N/A | Yes | High | Open | Current performance below plan | 180 | 180.0001

## Evidence
Evidence ID | Grant ID | Requirement ID | Task ID | Evidence Type | Document/Receipt URL | Submission Date | Submitted By | Confirmation/Receipt | Verified By | Verification Date | Status | Notes
E-001 | G-001 | R-001 | T-006 | Funder submission receipt |  |  | Associate Director |  |  |  | Missing | Synthetic placeholder
E-002 | G-001 | R-002 | T-004 | Financial report source |  |  | Finance Lead |  |  |  | Missing | Synthetic placeholder

## Issues
Issue ID | Grant ID | Requirement ID | Issue | Severity | Owner | Date Identified | Resolution | Escalation Status | Status | Source/Notes
I-001 | G-001 | R-001 | Participant data overdue | High | Program Director | 46276 |  | Escalated | Open | Dependency missed
I-002 | G-001 | R-002 | Financial data is stale | Critical | Finance Lead | 46276 |  | Escalated | Open | Last authoritative update >60 days
I-003 | G-002 | R-003 | Deliverable below expected trajectory | Medium | Program Director | 46276 |  | Open | Open | Management warning; not funder conclusion
I-004 | G-003 | R-004 | Renewal decision pending | Medium | Executive Director | 46276 |  | Open | Open | Decision needed this week

## Financials
Grant ID | Award Amount | Amount Spent | Committed Funds | Remaining Funds | Grant % Elapsed | Spend % | Last Authoritative Update | Days Stale | Financial Health | Management Warning | Authoritative Source URL
G-001 | 250000 | 112500 | 15000 | 122500 | 69.51% | 45% | 46223 | 53 | AT RISK | Potential underspending — review
G-002 | 125000 | 43000 | 9000 | 73000 | 44.78% | 34.4% | 46270 | 6 | HEALTHY
G-003 | 60000 | 8000 | 2500 | 49500 | 19.78% | 13.33% |  |  | UNKNOWN | Financial data missing or stale

## ProgramMetrics
Metric ID | Metric Name | Definition | Authoritative Source | Last Update | Value | Target | Unit | Freshness Days | Data Confidence | Used By Grants | Notes
PM-001 | Participants served | Unique participants meeting program definition | Program outcome system | 46266 | 78 | 100 | participants | 10 | CURRENT | G-001; G-002 | Reusable program metric
PM-002 | Successful stabilization rate | Funder-specific numerator/denominator rules | Program outcome system | 46249 | 0.61 | 0.7 | rate | 27 | CURRENT | G-002 | Confirm funder-specific definition before reuse

## SourceOfTruth
Information Type | Authoritative System | Dashboard Role | Sync Direction | Status | Implementation Note
Grant agreements / amendments | SharePoint / Google Drive (production TBD) | Link + extracted proposals only | Source → Dashboard | MANUAL/TBD | Do not duplicate document repository
Financial transactions / balances | Accounting system (TBD) | Read management indicators + freshness | Source → Dashboard | MANUAL/TBD | Never treat dashboard as accounting ledger
Structured grant requirements | Grant Dashboard datastore | Authoritative workflow record | Dashboard | ACTIVE | Verified requirements only
Tasks / dependencies | Grant Dashboard datastore | Authoritative workflow record | Dashboard | ACTIVE | Requirement ≠ Task
Calendar deadlines | Production calendar (TBD) | Scheduled representation | Two-way when safe | MANUAL/TBD | Use event IDs to prevent duplicates
Evidence / submission receipts | Existing document repository + dashboard links | Index + verification state | Source → Dashboard | MANUAL/TBD | Completion requires proof for important obligations
Program outcomes | Existing outcome system (TBD) | Reusable aggregate metrics | Source → Dashboard | MANUAL/TBD | Preserve funder-specific definitions
Email change notices | Production email (TBD) | Propose changes, never auto-authorize | Source → Proposed Change | MANUAL/TBD | Require human confirmation

## ChangeLog
Change ID | Timestamp | User | Entity Type | Entity ID | Field | Previous Value | New Value | Source/Evidence | Reason
C-001 | 46276.3333 | System Build | System | MVP | Initialization |  | Portable MVP created | User request | Initial build

## ActionQueue
Rank | Task ID | Grant | Action | Owner | Due | Why it needs attention | Score | Recommended Action
1 | T-004 | SAMPLE — Community Services Grant | Review financial report | Associate Director | 46279 | Finance source stale | 235 | Review / act
2 | T-006 | SAMPLE — Community Services Grant | Submit quarterly report | Associate Director | 46282 | External deadline | 220 | Review / act
3 | T-003 | SAMPLE — Community Services Grant | Draft narrative report | Associate Director | 46278 | Blocked by program data | 195 | Review / act
4 | T-008 | SAMPLE — Family Stabilization Grant | Review deliverable trajectory | Associate Director | 46280 | Current performance below plan | 180 | Review / act
5 | T-005 | SAMPLE — Capacity Building Grant | Make renewal go/no-go decision | Executive Director | 46281 | Leadership decision needed | 150 | Review / act
6 | T-002 | SAMPLE — Community Services Grant | Obtain current finance data | Finance Lead | 46276 | Required for report | 135 | Monitor owner / escalate by rule
7 | T-001 | SAMPLE — Community Services Grant | Obtain participant/program data | Program Director | 46275 | Program data was due yesterday | 135 | Monitor owner / escalate by rule
8 | T-007 | SAMPLE — Family Stabilization Grant | Refresh participant outcome metric | Program Director | 46303 |  | 25 | Monitor owner / escalate by rule
9
10
11
12
13
14
15
16
17
18
19
20

## Dashboard
GRANT MANAGEMENT — ACTION DASHBOARD
What needs my attention now, and can I trust that everything else is being tracked?
Portfolio Signal | Value |  | Trust Check
Active grants | 3 |  | Dimension | Status | Basis | Last/Next Check | Action
Open issues | 4 |  | Deadline Health | AT RISK | Overdue dependency exists | Daily | Review Action Queue
Critical action items | 5 |  | Financial Health | UNKNOWN | At least one stale/missing authoritative update | Daily | Request finance refresh
Unknown/stale financials | 1 |  | Compliance / Evidence | AT RISK | Required evidence missing on open obligations | Weekly | Verify evidence
TOP ACTIONS
Rank | Grant | Action | Owner | Due | Reason | Score | Next step
1 | SAMPLE — Community Services Grant | Review financial report | Associate Director | 2026-09-14 | Finance source stale | 235 | Review / act
2 | SAMPLE — Community Services Grant | Submit quarterly report | Associate Director | 2026-09-17 | External deadline | 220 | Review / act
3 | SAMPLE — Community Services Grant | Draft narrative report | Associate Director | 2026-09-13 | Blocked by program data | 195 | Review / act
4 | SAMPLE — Family Stabilization Grant | Review deliverable trajectory | Associate Director | 2026-09-15 | Current performance below plan | 180 | Review / act
5 | SAMPLE — Capacity Building Grant | Make renewal go/no-go decision | Executive Director | 2026-09-16 | Leadership decision needed | 150 | Review / act
6 | SAMPLE — Community Services Grant | Obtain current finance data | Finance Lead | 2026-09-11 | Required for report | 135 | Monitor owner / escalate by rule
CONFIDENCE STATEMENT
Attention remains required. Review the ranked queue and UNKNOWN/stale data before relying on the portfolio as fully current.
Health Dimension | G-001 | G-002 | G-003 | Meaning
Deadline Health | AT RISK | WATCH | HEALTHY | Based on deadlines + dependencies
Deliverable Health | WATCH | AT RISK | HEALTHY | Based on outcome trajectory
Financial Health | UNKNOWN | HEALTHY | UNKNOWN | UNKNOWN is distinct from healthy
Compliance Health | AT RISK | WATCH | HEALTHY | Based on verified obligations/evidence
Data Confidence | LOW | MEDIUM | LOW | Based on freshness + missing sources